RISK REGISTER & CLOSURE NOTE
PropTax – Online Property Tax Self-Assessment and Payment Portal

| Field | Details |
| --- | --- |
| Student Name | Ragini Singh |
| Roll No. | 150096724023 |
| Case Study No. | 141 |
| Case Study Title | PropTax – Online Property Tax Self-Assessment and Payment Portal |
| Subject | Software Engineering & Project Management |
| Semester | V |
| Examination | Sprint 1 Examination |
| Deliverable | Risk Register & Closure Note |

1. Risk Management Approach

Risks are assessed using Probability × Impact. Probability and impact are scored from 1 to 5. Exposure is calculated as P × I. Higher exposure risks receive earlier management attention. The risk register is kept separate from the issue log: a risk is a possible future event, while an issue is an event that has already occurred.

2. Risk Register

| ID | Risk | P | I | Exposure | Category | Mitigation / Response | Owner |
| --- | --- | --- | --- | --- | --- | --- | --- |
| R01 | Legal requirements for objections are unclear or change | 4 | 5 | 20 | Legal / Scope | Keep full objections outside Release 1; confirm legal rules before later implementation. | PM / Legal |
| R02 | Tax rate-table or rebate rules are incorrect or incomplete | 3 | 5 | 15 | Business / Quality | Validate rules with Revenue Department before calculation testing. | Revenue / Business |
| R03 | Payment gateway integration or confirmation fails | 3 | 5 | 15 | Technical / Integration | Test gateway early and define success/failure/reconciliation handling. | Technical Lead |
| R04 | Velocity remains below 11 points per sprint | 3 | 4 | 12 | Schedule | Track actual velocity and protect core Release 1 scope. | Project Manager |
| R05 | Security or unauthorized-access issue exposes data | 2 | 5 | 10 | Security | Apply access controls and security testing. | Technical / Security |
| R06 | Property data quality causes incorrect assessment | 3 | 4 | 12 | Data | Validate property data and flag inconsistent records. | Revenue / Data |
| R07 | Testing finds defects late | 3 | 3 | 9 | Quality | Run testing throughout development and prioritize critical defects. | QA / Testing |

3. Probability–Impact Matrix

Exposure is calculated as Probability × Impact. The Excel workbook contains the complete 5×5 matrix.

| Impact \ Probability | 1 | 2 | 3 | 4 | 5 |
| --- | --- | --- | --- | --- | --- |
| 1 | 1 | 2 | 3 | 4 | 5 |
| 2 | 2 | 4 | 6 | 8 | 10 |
| 3 | 3 | 6 | 9 | 12 | 15 |
| 4 | 4 | 8 | 12 | 16 | 20 |
| 5 | 5 | 10 | 15 | 20 | 25 |

For this register, R01 has the highest exposure (20). R02 and R03 have exposure 15. These are the top three risks used for RMMM.

4. Top 3 Risks – RMMM

| Risk | Mitigation | Monitoring | Management / Trigger | Contingency | Owner |
| --- | --- | --- | --- | --- | --- |
| R01 – Legal objection requirements | Keep objections outside Release 1 and obtain legal clarification. | Review legal clarification status each sprint. | If legal rules remain unclear at scope freeze, do not include objections. | Move objections to a later release and protect the 55-point core scope. | PM / Legal |
| R02 – Rate/rebate rules | Validate approved rules before finalizing calculation. | Review rule approval and calculation tests. | If a rule is disputed or changes, freeze affected calculation rule. | Hold affected calculation release until verified and retested. | Revenue / Business |
| R03 – Payment integration | Test gateway early and define success/failure handling. | Track gateway failures and confirmation mismatches. | If confirmation is unreliable, escalate before release validation. | Use failure/reconciliation path and prevent incorrect success marking. | Technical Lead |

5. Issue Log

Issues are different from risks because issues have already occurred. The accompanying workbook keeps the issue log separate. The sample issue entries are explicitly based on the worked-example defects used in the previous testing deliverable.

| Issue | Description | Action | Status |
| --- | --- | --- | --- |
| I01 | Worked-example rate-table calculation defect | Correct rule and rerun related tests | Closed |
| I02 | Worked-example failed-payment response had ambiguous status | Define explicit failure status and reconciliation handling | Closed |

6. Closure Note

The PropTax case study was planned as an individual software engineering and project management exercise covering requirements, design, estimation, testing, risk management and release planning.

The Release 1 plan focuses on property search, self-assessment, tax calculation, online payment and receipt generation. The supplied backlog for this core scope is 55 story points. At a velocity of 11 points per 2-week sprint, the forecast is 5 sprints or 10 weeks.

The full objections workflow adds 29 points, bringing the total to 84 points. At the supplied velocity this requires 8 sprints, or 16 weeks, which consumes the entire available window before the tax year starts. The case study also identifies legal complexity in objections, so the full objection workflow is planned for a later release.

The project artefacts produced for this case study include the SRS, UML package, project plan, forecast sheet, test plan and evidence, risk register and closure note.

7. Lessons Learned

Requirements should be clearly defined before detailed design and implementation.

Scope decisions should consider effort, deadline, legal complexity and quality rather than functionality alone.

Using the supplied velocity and story points makes the schedule decision transparent.

Boundary-value, equivalence-class and decision-table testing help cover different classes of input and business rules.

Risks should be identified early, ranked using probability and impact, and assigned clear owners.

Risks and already-occurred issues should be tracked separately.

8. Closure Statement

The case study planning is considered complete for the defined Release 1 scope, subject to actual implementation, test execution and stakeholder validation. Future releases can address the full legal objection workflow after the required legal rules and acceptance criteria are available.