## Forecast Sheet
PropTax – Forecast Sheet ¦ Case Study 141
Student Name | Ragini Singh
Roll No. | 150096724023
Case Study No. | 141
Case Study Title | PropTax – Online Property Tax Self-Assessment and Payment Portal
Subject | Software Engineering & Project Management
Semester | V
Examination | Sprint 1 Examination
Given Project Data
Search & Calculator | 34 points
Payment & Receipts | 21 points
Objections Workflow | 29 points
Velocity | 11 points per 2-week sprint
Tax year starts | 16 weeks
Online target | 35% of payments in Year 1
Forecast – Without Objections (Release 1)
Search & Calculator | 34
Payment & Receipts | 21
Total Story Points
Velocity (points/sprint) | 11
Sprint Length (weeks) | 2
Sprints Required
Rounded Sprints | 5
Estimated Duration (weeks)
Available Window (weeks) | 16
Schedule Buffer (weeks)
Forecast – With Objections
Search & Calculator | 34
Payment & Receipts | 21
Objections Workflow | 29
Total Story Points
Velocity (points/sprint) | 11
Sprint Length (weeks) | 2
Exact Sprints Required
Rounded Sprints | 8
Estimated Duration (weeks)
Available Window (weeks) | 16
Schedule Buffer (weeks)
Comparison
Scope | Story Points | Exact Sprints | Rounded Sprints | Duration | Buffer vs 16 weeks
Without objections | 55 |  | 5
With objections | 84 |  | 8
Assumptions & Confidence
• Velocity remains constant at 11 points per 2-week sprint.
• Story-point estimates supplied by the case study are used without modification.
• Partial sprint is rounded up to the next complete sprint for delivery forecasting.
• The 16-week tax-year start is treated as the available schedule window.
• No calendar start date is supplied, so the forecast is expressed in weeks and sprints.
• The forecast is an estimate, not a delivery promise.
Confidence Level | Medium confidence — the case study provides backlog points, velocity and the 16-week window, but does not provide historical velocity variance, task-level estimates or a calendar start date.

## Step-by-Step Calculations
Step-by-Step Forecast Calculations
Calculation | Formula | Result | Explanation
Without Objections | 34 + 21 | 55 points | Search & Calculator + Payment & Receipts
Sprints | 55 / 11 | 5 sprints | Total points ÷ velocity
Duration | 5 × 2 | 10 weeks | Sprints × sprint length
Buffer | 16 - 10 | 6 weeks | Available window - estimated duration
With Objections | 34 + 21 + 29 | 84 points | Adds objections workflow
Exact sprints | 84 / 11 | 7.636... | Total points ÷ velocity
Rounded sprints | ceil(7.636...) | 8 sprints | Partial sprint rounded up
Duration | 8 × 2 | 16 weeks | Sprints × sprint length
Buffer | 16 - 16 | 0 weeks | Available window - estimated duration