## Risk Register
PropTax – Risk Register ¦ Case Study 141
Student | Ragini Singh
Roll No. | 150096724023
Case Study | 141
Title | PropTax – Online Property Tax Self-Assessment and Payment Portal
Subject | Software Engineering & Project Management
Semester | V
Risk ID | Risk | Probability (1–5) | Impact (1–5) | Exposure P×I | Rank | Category | Mitigation | Contingency | Owner | Status
R01 | Legal requirements for objections are unclear or change | 4 | 5 |  | High | Legal / Scope | Keep full objections workflow outside Release 1; confirm legal rules before future implementation. | If legal clarification is delayed, defer objections to a later release. | Project Manager / Legal stakeholder | Open
R02 | Tax rate-table or rebate rules are incorrect or incomplete | 3 | 5 |  | High | Business / Quality | Validate rate-table and rebate rules with the Revenue Department before calculation testing. | Freeze calculation scope and block release of affected calculation rules until verified. | Revenue / Business Owner | Open
R03 | Payment gateway integration or confirmation fails | 3 | 5 |  | High | Technical / Integration | Define payment success/failure handling and test gateway integration early. | Provide clear failed-payment status and reconciliation path; do not mark unpaid transactions as successful. | Technical Lead | Open
R04 | Velocity remains below 11 points per sprint | 3 | 4 |  | Medium | Schedule | Track actual sprint velocity and review progress each sprint. | De-scope lower-priority work and protect core Release 1 scope. | Project Manager | Open
R05 | Security or unauthorized-access issue exposes data | 2 | 5 |  | Medium | Security | Apply access controls, secure communication and security testing. | Block affected functionality, remediate issue and retest before release. | Technical / Security Owner | Open
R06 | Property data quality causes incorrect assessment | 3 | 4 |  | Medium | Data | Validate property data and provide input validation. | Flag inconsistent records for review rather than calculating silently. | Revenue / Data Owner | Open
R07 | Testing finds defects late in the release | 3 | 3 |  | Medium | Quality | Run BVA, equivalence, decision-table and integration tests during development. | Prioritize critical defects and delay non-essential features if necessary. | QA / Testing | Open

## Probability Impact Matrix
Probability–Impact Matrix
Impact \ Probability | 1 | 2 | 3 | 4 | 5
5 | 5 | 10 | 15 | 20 | 25
4 | 4 | 8 | 12 | 16 | 20
3 | 3 | 6 | 9 | 12 | 15
2 | 2 | 4 | 6 | 8 | 10
1 | 1 | 2 | 3 | 4 | 5
Exposure = Probability × Impact. Higher exposure receives earlier management attention.

## Top 3 RMMM
Top 3 Risks – RMMM
Risk | Mitigation | Monitoring | Management / Trigger | Contingency | Owner | Trigger Metric | Status
R01 | Keep objections outside Release 1; obtain legal clarification for later release. | Review legal clarification status each sprint. | If legal rules are still unclear before scope freeze, do not include objections. | Move objections to later release and protect core 55-point scope. | PM / Legal | Legal requirements confirmed? | Open
R02 | Validate approved rate and rebate rules before coding is finalized. | Review rule approval and calculation test results. | If a rule is disputed or changes, freeze affected calculation rule. | Hold affected calculation release until verified and retested. | Revenue / Business | Approved rule set available? | Open
R03 | Test payment integration early; define success/failure/reconciliation behavior. | Track gateway test failures and confirmation mismatches. | If payment confirmation is unreliable, escalate before release validation. | Use failure status/reconciliation path and block incorrect success marking. | Technical Lead | Gateway success/confirmation match rate | Open

## Issue Log
Issue Log – Separate from Risk Register
Issue ID | Issue / Event | Impact | Action Taken | Owner | Status
I01 | A defect was found in a worked-example rate-table calculation test. | Incorrect tax amount if released. | Correct calculation rule and rerun related tests. | Development / QA | Closed
I02 | A failed-payment response showed an ambiguous status in the worked example. | User could misunderstand payment status. | Define explicit failed status and reconciliation handling. | Technical Lead | Closed